## Sheet1
Disciplines	Activities	Tasks				Projected	1/14 – 1/20	1/21 – 1/27	1/28 – 2/3	2/4 – 2/10	2/11 – 2/17	2/18 – 2/24	2/25 – 3/3	3/4 – 3/10	3/11 – 3/17	Total
Business Modeling						9.5	3.5	0	0	2	1	0	0	0	0	6.5
	Understand the business environment
		Interview stakeholders.				3	1			0.5	0.5					2
		Evaluate existing architecture.				1	0.5									0.5
	Create the system vision
		Generate a list of primary business benefits.				0.5				0.5						0.5
		Develop a list of system capabilities.				2	1				0.5					1.5
	Create business models
		Identify business events.				1.5	0.5			0.5						1
		Define information and data flow models				1.5	0.5			0.5						1
Requirements						53	3	0	0	1	0.5	2.5	0	7	4.5	18.5
	Gather detailed information
		Analyze current system.				3	1								0.5	1.5
		Interview stakeholders.				4	2			1	0.5					3.5
	Define functional requirements
		Create event decomposition table.				2								1		1
		Create use case diagram.				2								1		1
		Write use case descriptions.				8								4	3	7
		Create problem domain class diagram.				2								1		1
		Create interaction diagram.				1									0.5	0.5
	Define nonfunctional requirements
		Define security requirements.				2									0.5	0.5
		Define reliability requirements.				2										0
		Define technological requirements.				2										0
		Define usability requirements.				2										0
	Prioritize requirements
		Determine core requirements.				3										0
		Schedule requirements across iterations.				2										0
	Develop user interface dialogs
		Create storyboards.				8										0
		Determine if changes to existing design are needed.				4						2				2
	Evaluate requirements with users
		Interview stakeholders with requirements.				3						0.5				0.5
		Revise requirements as needed.				3										0
Disciplines	Activities	Tasks				Projected	1/14 – 1/21	1/21 – 1/28	1/28 – 2/4	2/4 – 2/11	2/11 – 2/17	2/18 – 2/24	2/25 – 3/3	3/4 – 3/10	3/11 – 3/17	Total
Design						67	0.5	2	0	0.5	0	0.5	0	0	1	4.5
	Design the support services architecture and deployment environment
		Plan production server setup.				3	0.5									0.5
		Find or design acceptable hosting solution.				4				0.5						0.5
	Design the software architecture
		Establish model, view, controller architecture details.				4		1							1	2
		Design package diagrams.				3										0
	Design use case realizations
		Create design class diagram.				5										0
		Create sequence diagrams.				12										0
	Design the database
		Finalize domain class diagram.				2										0
		Specify relationships between domain classes.				2										0
	Design the system and user interfaces
		Review storyboards.				3										0
		Design view logic.				5		0.5								0.5
		Design Django templates.				3		0.5				0.5				1
		Design RSS and social networking interfaces.				8										0
		Review interface design details with stakeholders.				3										0
	Design the system security and controls
		Determine security groups and access levels.				8										0
		Design login page.				2										0
Implementation						69	0	4.5	6.5	0	0	3	0	0	3	17
	Build software components
		Build models.				20		0.5	2.5						2	5
		Build view logic.				10		0.5	1						1	2.5
		Build templates.				20		0.5	1			2				3.5
		Write URL configuration files.				5			0.5							0.5
		Write settings files.				5		0.5	0.5							1
	Acquire software components
		Download and install python libraries.				2		1								1
		Download and install Django.				2		1								1
		Download and install any needed Django modules.				2			0.5							0.5
	Integrate software components
		Configure deployment software on test server.				1		0.5				0.5				1
		Deploy full system on test server.				2			0.5			0.5				1
Disciplines	Activities	Tasks				Projected	1/14 – 1/21	1/21 – 1/28	1/28 – 2/4	2/4 – 2/11	2/11 – 2/17	2/18 – 2/24	2/25 – 3/3	3/4 – 3/10	3/11 – 3/17	Total
Testing						40	0	0	0	0	0	0	0	0	0	0
	Define and conduct unit testing
		Define unit tests.				5										0
		Conduct core function unit tests.				5										0
		Conduct support function unit tests.				4										0
	Define and conduct integration testing
		Define integration tests.				5										0
		Conduct integration tests.				8										0
	Define and conduct usability testing
		Review design specifications against implementation.				2										0
		Conduct usability testing with users.				3										0
	Define and conduct user acceptance testing
		Have administrators test administration functions.				5										0
		Review non-administrative functions with users.				3										0
Deployment						31	0	0	0	0	0	0	0	0	0	0
	Acquire hardware and system software
		Purchase hosting package or setup server hardware.				5										0
		Install and configure system software as needed.				5										0
	Package and install components
		Deploy finished system to production server.				1										0
		Configure system on production server.				1										0
	Train users
		Develop training documentation for system.				5										0
		Hands-on training.				5										0
	Convert and initialize data
		Add initial users to system.				1										0
		Import existing information.				8										0
Disciplines	Activities	Tasks				Projected	1/14 – 1/21	1/21 – 1/28	1/28 – 2/4	2/4 – 2/11	2/11 – 2/17	2/18 – 2/24	2/25 – 3/3	3/4 – 3/10	3/11 – 3/17	Total
Project Management						22.5	3.5	0	0	8.5	0.2	0.2	0.2	0.2	0.2	13
	Evaluate the project’s scope and risk
		Create initial problem domain class list.				1	0.75			0.25						1
		Create initial primary use case list.				1	0.75			0.25						1
		Review project scope and evaluate risks and threats.				2				1						1
	Confirm the project’s feasibility
		Calculate economic feasibility.				1				1						1
		Evaluate technical feasibility.				1	1									1
		Evaluate schedule feasibility.				1				1						1
	Develop the project and iteration schedules
		List out activity tasks.				2				2						2
		Review with Dr. Satzinger.				0.5										0
	Monitor and control the project’s iterations
		Keep log of time spent on tasks.				5				1	0.2	0.2	0.2	0.2	0.2	2
		Create periodic reports for Dr. Satzinger.				8	1			2						3
Configuration and Change Management						8	0	2	0.25	0	0	0.5	0	0	0	2.75
	Develop change control procedures
		Setup SVN procedures.				1		1								1
		Develop plan for release to test & production servers.				2		1				0.5				1.5
	Manage models and software components
		Update models as needed.				2										0
		Keep proper, detailed revision documentation.				3			0.25							0.25
Environment						16	0.5	2	1	1	0.5	0	0	0	1	6
	Select and configure the development tools
		Install python and Django on development machine.				1		1								1
		Create a SVN repository.				1		1								1
		Install system software on test server.				0										0
		Configure test server.				2			1							1
	Tailor the UP development process
		Setup of deliverables.				3				0.5					1	1.5
		Meeting with Dr Satzinger.				3	0.5			0.5	0.5					1.5
	Provide technical support services
		Provide support to test users.				3										0
		Provide support for development environment.				3										0
Total						316	11	10.5	7.75	13	2.2	6.7	0.2	7.2	9.7	68.25